## Sheet1
Color Coding |  |  | Completed |  |  |  | FALL 2019 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2019-09-10 | 2019-09-17 | 2019-09-24 | 2019-10-01 | 2019-10-08 | 2019-10-15 | 2019-10-22 | 2019-10-29 | 2019-11-05 | 2019-11-12 | 2019-11-19 | 2019-11-26 | 2019-12-03 | 2019-12-10 | 2019-12-17
Project Phase | Activity |  | Resource Type | Start Date | End Date | Progress %
Project Initiation | Project proposal discussion |  | Purti Choudhary | 2019-09-11 | 2019-09-16 | 100%
| Prioritize project ideas |  | Purti Choudhary | 2019-09-11 | 2019-09-16 | 100%
| Estimation of cost and schedule |  | Aniket Munim | 2019-09-13 | 2019-09-16 | 100%
| Development of the business case |  | Purti Choudhary | 2019-09-13 | 2019-09-17 | 100%
| Project environment preparation |  | Aniket Munim | 2019-09-17 | 2019-09-20 | 100%
MILESTONE 1: INITIAL PROJECT PLAN
Requirement Analysis | Production of project schedule |  | Purti Choudhary | 2019-09-11 | 2019-09-16 | 100%
| Determine project features |  | Aniket Munim | 2019-09-17 | 2019-09-21 | 100%
| Organize Project Team |  | Aniket Munim | 2019-09-19 | 2019-09-23 | 100%
| Definition of Software Methodology |  | Samiksha Mathur | 2019-09-20 | 2019-09-23 | 100%
| Gathering of Business Requirements |  | Samiksha Mathur | 2019-09-24 | 2019-09-29 | 100%
| Business Requirements Analysis |  | Samiksha Mathur | 2019-09-24 | 2019-09-30 | 100%
| System Requirements definition |  | Samiksha Mathur | 2019-09-24 | 2019-09-20 | 100%
| Requirements prioritization |  | Purti Choudhary | 2019-09-24 | 2019-09-30 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design |  | Aditya Gajjar | 2019-11-05 | 2019-11-12 | 0%
| Database Design |  | Lakshmi Chamarathi | 2019-10-29 | 2019-11-05 | 0%
| System Interface Design |  | Aditya Gajjar | 2019-11-05 | 2019-11-12 | 0%
| User interface design |  | Aditya Gajjar | 2019-11-12 | 2019-11-19 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | User Portal | GUI & Functionality Design | Amrit Choudhary | 2019-10-15 | 2019-10-29 | 0%
|  | Coding | Amrit Choudhary | 2019-10-15 | 2019-10-29 | 0%
| Admin Portal | GUI & Functionality Design | Anil Bandari | 2019-10-29 | 2019-11-05 | 0%
|  | Coding | Anil Bandari | 2019-10-20 | 2019-11-05 | 0%
| ToGo Delivery | GUI & Functionality Design | Amrit Choudhary | 2019-11-05 | 2019-11-12 | 0%
|  | Coding | Amrit Choudhary | 2019-11-05 | 2019-11-12 | 0%
| Pickup & Drop | GUI & Functionality Design | Anil Bandari | 2019-11-12 | 2019-11-19 | 0%
|  | Coding | Amrit Choudhary | 2019-11-12 | 2019-11-19 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Overall Testing Strategy |  |  | 2019-11-05 | 2019-12-03 | 0%
| Evaluate Features to be Tested |  | ALL | 2019-11-05 | 2019-12-03 | 0%
| User Portal | Design Test Cases | Lakshmi Chamarathi | 2019-11-05 | 2019-11-12 | 0%
|  | Execute Test Cases | Khaja Nazish | 2019-11-12 | 2019-11-19 | 0%
|  | Anaylze Test Results | Aditya Gajjar | 2019-11-19 | 2019-11-26 | 0%
| Admin Portal | Design Test Cases | Khaja Nazish | 2019-11-05 | 2019-11-12 | 0%
|  | Execute Test Cases | Aditya Gajjar | 2019-11-12 | 2019-11-19 | 0%
|  | Anaylze Test Results | Aditya Gajjar | 2019-11-12 | 2019-11-26 | 0%
| ToGo Delivery | Design Test Cases | Khaja Nazish | 2019-11-05 | 2019-11-12 | 0%
|  | Execute Test Cases | Aditya Gajjar | 2019-11-12 | 2019-11-19 | 0%
|  | Anaylze Test Results | ALL | 2019-11-19 | 2019-11-26 | 0%
| Pickup & Drop | Design Test Cases | Lakshmi Chamarathi | 2019-11-05 | 2019-11-12 | 0%
|  | Execute Test Cases | Khaja Nazish | 2019-11-12 | 2019-11-19 | 0%
|  | Anaylze Test Results | ALL | 2019-11-19 | 2019-11-26 | 0%
Implementation | Deploy Application For Presentation Demo |  | Amrit Choudhary Anil Bandari | 2019-12-03 | 2019-12-10 | 0%
MILESTONE 5: TESTING COMPLETED
Presentation | Prepare Presentation of Demo |  | ALL | 2019-12-10 | 2019-12-17