## Sheet1
Project Roles
Process Area | Project Tasks | Project Manager | Project Owner | Lead Developer | Developer | Business Analyst | Lead QA Analyst | Tester | DBA
Project Management | Develop a project plan | A, R | C | C | I | C, I | C | I | I
| Provide cost estimate | A, R | R | I | I | I | I | I | I
| Maintain project risk and issue log | A | R | C | C | C | C | C | C
| Provide project status report | A | R | C | I | C, I | C | I | I
Requirements | Perform requirement analysis | A | I | C | I | R, I | I | I | I
| Gather business requirements | A | I | C | I | R, C | I | I | I
| Produce functional requirements | A | I | C | C | R | C | I | I
Design | Produce high-level design specs | A | I | R | C | C | I | I | C
| Produce data model | A | I | C | C | C | I | I | R
| Produce detailed design specs | A | I | R | R | C | I | I | R
Coding | Establish code repository | A | I | R | R | I | I | I | I
| Develop component code | A | I | R | R | I | I | I | I
Testing | Develop test plan | A | I | C | I | C | R | C | C
| Establish a test repository | A | I | C | I | I | R | C | I
| Develop test specifications | A | I | I | I | I | R | R | I
| Execute tests, report defects | A | I | I | I | I | R | R | I
| Conduct defect review calls | A | I | C | I | C | R | C | C
| Produce, deliver defect metrics | A | C | C | I | C | R | C | I
| Support test environments | A | I | R | R | I | C | I | R
Deployment | Produce a development plan | A | I | R | R | I | I | I | R
| Produce development procedures | A | I | R | R | I | I | I | R
| Deploy software into production | A | I | R | R | I | C | C | R