## R2 I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I3 | 04. Payment | 4.03 | Add a new credit card | Implement validation to different fields (Credit card number, Name on card, Expiry date, Security Code) is provided in the application | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
2 | R2 - I3 | 04. Payment | 4.03 | Add a new credit card | Implement validation to ensure all the fields appear correctly on different mobile devices. | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
3 | R2 - I3 | 04. Payment | 4.03 | Add a new credit card | Implement validation to ensure the user has logged into his account in order to add an credit card | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
4 | R2 - I3 | 04. Payment | 4.03 | Add a new credit card | Implement validation to ensure that user can type only numerical values for credit card number, expiry date and security code | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
5 | R2 - I3 | 04. Payment | 4.03 | Add a new credit card | Implement validation to ensure credit card details is saved in the system for the future refrences of the user | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
|  | 04. Payment | 4.03 | Add a new credit card | Implement validation to ensure that if user leave any of the field empty then system doesn't allow them to proceed further | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
|  | 04. Payment | 4.03 | Add a new credit card | Implement validation to ensure that user can type only alphabetic value for name on card field | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
7 | R2 - I3 | 04. Payment | 4.03 | Add a new credit card | Crosscut: Field Validation | 2020-04-11 | 2020-04-16 | 100% | Anil, Samiksha
9 | R2 - I3 | 04. Payment | 4.03 | Add a new credit card | Execute testing for the choosen crosscutting concerns | 2020-04-11 | 2020-04-16 | 100% | Purti, Samiksha
10 | R2 - I3 | 04. Payment | 4.02 | Make a Payment | Implement validation to ensure Payment service is provided in Make a Payment | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
11 | R2 - I3 | 04. Payment | 4.02 | Make a Payment | Implement validation to ensure payment is being made from the credit card details given by the user | 2020-04-11 | 2020-04-16 | 100% | Aditya, Amrit
12 | R2 - I3 | 04. Payment | 4.02 | Make a Payment | Implement validation that the paytment gets completed for the order amount | 2020-04-11 | 2020-04-16 | 100% | Anil, Aniket
13 | R2 - I3 | 04. Payment | 4.02 | Make a Payment | Implement validation to ensure correct amount get carried out from the order details to the payment confirmation page | 2020-04-11 | 2020-04-16 | 100% | Nazish, Aniket
14 | R2 - I3 | 04. Payment | 4.02 | Make a Payment | Crosscut: Field Validation, Data Dependency Validation | 2020-04-11 | 2020-04-16 | 100% | Samiskha, Lakshmi
15 | R2 - I3 | 04. Payment | 4.02 | Make a Payment | Execute testing for the choosen crosscutting concerns | 2020-04-11 | 2020-04-16 | 100% | Purti, Nazish
19 | R2 - I3 | 04. Payment | 4.01 | Payment Mode | Implement validation to ensure different payment options (Credit card / Debit card) has been provided to the user | 2020-04-17 | 2020-04-23 | 100% | Aditya, Amrit
19 | R2 - I3 | 04. Payment | 4.01 | Payment Mode | Implement validation to ensure that user is logged in and has added some items for order before processing to choose payment mode. | 2020-04-17 | 2020-04-23 | 100% | Aditya, Amrit
20 | R2 - I3 | 04. Payment | 4.01 | Payment Mode | Implement validation to ensure the drop down options appear correctly on different mobile devices | 2020-04-17 | 2020-04-23 | 100% | Aditya, Amrit, Anil
21 | R2 - I3 | 04. Payment | 4.01 | Payment Mode | Implement validation to ensure correct payment mode gets selected accoding to what the user selects | 2020-04-17 | 2020-04-23 | 100% | Aditya, Amrit, Nazish
22 | R2 - I3 | 04. Payment | 4.01 | Payment Mode | Crosscut: Entitlements | 2020-04-17 | 2020-04-23 | 100% | Samiksha, Anil
24 | R2 - I3 | 04. Payment | 4.01 | Payment Mode | Execute testing for the choosen crosscutting concerns | 2020-04-17 | 2020-04-23 | 100% | Purti, Aniket

## R2 I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Implement validation to ensure all the fields appear correctly on different mobile devices. | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
2 | R2 - I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Implement field validation for tracking id | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
3 | R2 - I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Implementation to ensure that a user is logged in and has placed an order before going to track the delivery status | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
4 | R2 - I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Implement to generate a random value for tracking id, everytime an order has been placed | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
5 | R2 - I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Implement validation to ensure user can enter only digits for the tracking id field | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
6 | R2-I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Implement the validation that tracking status will be shown only for valid tracking id | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
7 | R2-I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Crosscut: Field Validation | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
8 | R2-I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Implement validation to ensure it shows an estimated dellivery data and it should be a future date | 2020-05-01 | 2020-05-07 | 100% | Anil, Samiksha
9 | R2 - I4 | 03. Tracking Orders | 3.01 | Track the delivery status | Execute testing for the choosen crosscutting concerns | 2020-05-01 | 2020-05-07 | 100% | Purti, Samiksha
10 | R2 - I4 | 05. User Account | 5.04 | Review Delivered and to be Delivered items | Implement validation to ensure user need to login and place order before going to the review page | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
11 | R2 - I4 | 05. User Account | 5.04 | Review Delivered and to be Delivered items | Implement validation to ensure all the fields( Vehicle charges, Name/Type of item, Number of items, Description of item, Total distance, Delivery date) appear correctly on different mobile devices. | 2020-05-01 | 2020-05-07 | 100% | Aditya, Amrit
12 | R2 - I4 | 05. User Account | 5.04 | Review Delivered and to be Delivered items | Implement validation all the fields are read only and cannot be changed by user. | 2020-05-01 | 2020-05-07 | 100% | Anil, Aniket
13 | R2 - I4 | 05. User Account | 5.04 | Review Delivered and to be Delivered items | Implement validation that current order details and description gets displayed on the review page. | 2020-05-01 | 2020-05-07 | 100% | Nazish, Aniket
14 | R2 - I4 | 05. User Account | 5.04 | Review Delivered and to be Delivered items | Crosscut: Entitlements | 2020-05-08 | 2020-05-15 | 100% | Samiskha, Lakshmi
15 | R2 - I4 | 05. User Account | 5.04 | Review Delivered and to be Delivered items | Execute testing for the choosen crosscutting concerns | 2020-05-08 | 2020-05-15 | 100% | Purti, Nazish
19 | R2 - I4 | 03. Tracking Orders | 3.02 | Notification of delivered item | Implement validation to user must be logged in and placed an order to track status and receive notification | 2020-05-08 | 2020-05-15 | 100% | Aditya, Amrit
19 | R2 - I4 | 03. Tracking Orders | 3.02 | Notification of delivered item | Implement validation to ensure user can see the status of the placed order as Order is being prepared, On its way, Delivered etc. | 2020-05-08 | 2020-05-15 | 100% | Aditya, Amrit
20 | R2 - I4 | 03. Tracking Orders | 3.02 | Notification of delivered item | Implement validation to ensure that the user gets notified once the order gets delivered. | 2020-05-08 | 2020-05-15 | 100% | Aditya, Amrit, Anil
21 | R2 - I4 | 03. Tracking Orders | 3.02 | Notification of delivered item | Crosscut: Entitlements | 2020-05-08 | 2020-05-15 | 100% | Aditya, Amrit, Nazish
22 | R2 - I4 | 03. Tracking Orders | 3.02 | Notification of delivered item | Execute testing for the choosen crosscutting concerns | 2020-05-08 | 2020-05-15 | 100% | Samiksha, Anil