## R1 I1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Implement validation to ensure To-Go service is provided in the mentioned pickup location | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
2 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Implement validation to ensure correct pickup location is mentioned: Correct location must be provided with the Zip Code | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
3 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Implement validation to ensure the user has logged into his account in order to enter pickup location | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
4 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Implement validation to ensure accurate user access privileges: The user must be logged in to enter the pickup location or save the location | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
5 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Implement validation to ensure that accurate pickup location is marked on the map to pickup the items that have to be delivered. | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
6 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Implement validation to ensure Pickup location data is saved in the system for the future references of user | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
7 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Crosscut: Data Flow In | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
8 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Create test cases for functionality | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
9 | R1 - I1 | 01. To-Go Delivery | 1.01 | Mention Pickup Location | Execute test cases and document the test execution log | 2020-02-21 | 2020-02-28 | 100% | Purti Choudhary, Aditya Gajjar
10 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Implement delete functionality | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
11 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Create a button to delete account | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
12 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Implement validation before deletion (users and admin can only delete) | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
13 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Confirm the user's decision to delete the account | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
14 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Implement validation on fields to ensure that the account is deleted and removed from the database | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
15 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Crosscuts: Entitlements, Exception Handling | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
16 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Crosscuts: EXH - Exception Handling. Implement validation on fields to ensure error message is displayed if the user tries to login into his account after deletion. | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
17 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Create test cases for functionality | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
18 | R1 - I1 | 05. User's Account | 5.07 | Delete an Account | Execute test cases and document the test execution log | 2020-02-21 | 2020-02-28 | 100% | Anil Bandari, Aniket
19 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Implement validation to ensure To-Go service is provided in the mentioned delivery location | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
20 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Implement validation to ensure correct delivery location is mentioned: Correct location must be provided with the Zip Code | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
21 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Implement validation to ensure the user cannot mention the delivery location without entering the pickup location | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
22 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Implement validation to ensure the user has logged into his account in order to enter delivery location | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
23 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Implement validation on fields to ensure accurate user access privileges: The user must be logged in to enter the delivery location or save the location | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
24 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Implement validation to ensure that accurate delivery location is marked on the map to drop the items that has to be delivered. | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
25 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Crosscut: Data Flow in | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
26 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Create test cases for functionality | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
27 | R1 - I1 | 01. To-Go Delivery | 1.02 | Mention the delivery location | Execute test cases and document the test execution log | 2020-02-28 | 2020-03-06 | 100% | Lakshmi, Aditya Gajjar
28 | R1 - I1 | 02. Item Details | 2.01 | Enter details of the item | Implement validation on fields to ensure that the user can enter the details for an item only after mentioning the pickup and delivery location | 2020-02-28 | 2020-03-06 | 100% | Samiksha, Anil Bandari
29 | R1 - I1 | 02. Item Details | 2.01 | Enter details of the item | Implement validation on fields to ensure that at a time only details for one item are specified | 2020-02-28 | 2020-03-06 | 100% | Samiksha, Anil Bandari
30 | R1 - I1 | 02. Item Details | 2.01 | Enter details of the item | Crosscut: Field Validation | 2020-02-28 | 2020-03-06 | 100% | Samiksha, Anil Bandari
31 | R1 - I1 | 02. Item Details | 2.01 | Enter details of the item | Create test cases for functionality | 2020-02-28 | 2020-03-06 | 100% | Samiksha, Anil Bandari
32 | R1 - I1 | 02. Item Details | 2.01 | Enter details of the item | Execute test cases and document the test execution log | 2020-02-28 | 2020-03-06 | 100% | Samiksha, Anil Bandari

## R1 I2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Implement validation to ensure Number of items field is provided in the To-Go application | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
2 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Implement validation to ensure the fields appears correctly on different mobile devices. | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
3 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Implement validation to ensure that the user cannot enter more than 10 items at a time. | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
4 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Implement validation to ensure that only numerical value can be entered in the Number of items text field | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
5 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Crosscut: FV - Field Validation | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
6 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Create test cases for functionality | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
7 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Create test cases for validation | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
8 | R1 - I2 | 02. Item Details | 2.02 | Number of items to be delivered | Execute test cases and document the test execution log | 2020-03-20 | 2020-03-27 | 100% | Samiksha, Purti Choudhary
9 | R1 - I2 | 02. Items Details | 2.03 | Book a vehicle | Implement validation to ensure the icons to book the vehicle are provided in the To-Go application | 2020-03-20 | 2020-03-27 | 100% | Anil Bandari, Lakshmi
10 | R1 - I2 | 02. Items Details | 2.03 | Book a vehicle | Implement validation to ensure the vehicle icons appear correctly on different mobile devices. | 2020-03-20 | 2020-03-27 | 100% | Anil Bandari, Lakshmi
11 | R1 - I2 | 02. Items Details | 2.03 | Book a vehicle | Implement validation to ensure that the Vehicle Charges field is also present along with book the vehicle icons | 2020-03-20 | 2020-03-27 | 100% | Anil Bandari, Lakshmi
12 | R1 - I2 | 02. Items Details | 2.03 | Book a vehicle | Crosscut: EX - Exception Handling | 2020-03-20 | 2020-03-27 | 100% | Anil Bandari, Lakshmi
13 | R1 - I2 | 02. Items Details | 2.03 | Book a vehicle | Create test cases for functionality | 2020-03-20 | 2020-03-27 | 100% | Anil Bandari, Lakshmi
14 | R1 - I2 | 02. Items Details | 2.03 | Book a vehicle | Execute test cases and document the test execution log | 2020-03-20 | 2020-03-27 | 100% | Anil Bandari, Lakshmi
15 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Implement validation to ensure that email, password and confirm password fields are present on modify user information page. | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
16 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Implement validation to ensure the fields appear correctly on different mobile devices. | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
17 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Implement validation on fields to ensure accurate modifications: Email Address is required and not null/blank | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
18 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Implement validation on fields to ensure accurate modifications: Password needs to meet validation criteria | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
19 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Implement validation on fields to ensure accurate modifications: Confirm Password when password is updated. | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
20 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Display whether the query of the account information was processed successfully. | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
21 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Crosscut: FV - Field Validation | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
22 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Create test cases for functionality | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
23 | R1 - I2 | 05. User's Account | 5.03 | Modify General User's Information | Execute test cases and document the test execution log | 2020-03-27 | 2020-04-03 | 70% | Lakshmi, Aditya Gajjar
24 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Implement validation to ensure 3 types of subscription plan options along with their description are available | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari
25 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Implement validation to ensure all the subscription plans have a submit button at the bottom to enable the user to choose the subscription plan | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari
26 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Implement validation to ensure all the fields appear correctly on different mobile devices. | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari
27 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Implement validation to ensure accurate choice of plan: User should be subscribed with the chosen subscription plan and payment should be calculated accordingly | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari
28 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Implement validation to ensure executing the tests for all the applicable internal and external users to ensure it works in the expected way. | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari
29 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Crosscut: EN- Entitlements | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari
30 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Create test cases for functionality | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari
31 | R1 - I2 | 05. User's Account | 5.05 | Choose a Subscription Plan | Execute test cases and document the test execution log | 2020-03-27 | 2020-04-03 | 100% | Purti Choudhary, Anil Bandari