## Road Map I1
ToGo Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/06/20 | Iteration 2 - 04/03/20 | Iteration 3 - 04/24/20 | Iteration 4 - 05/01/20
Module 1 - ToGo Delivery | 01.01 Mention the location of pickup | 3 | x
| 01.02 Mention the delivery location | 3 | x
Module 2- Item Details | 02.01 Enter details of the item | 2 | x
| 02.02 Enter the number of items to be delivered | 2 |  | x
| 02.03 Book a vehicle | 4 |  | x
Module 3 - Tracking orders | 03.01 Track the delivery status | 4 |  |  |  | x
| 03.02 Notification of the delivered item | 3 |  |  |  | x
Module 4 - Payment | 04.01 Payment Mode | 5 |  |  | x
| 04.02 Make a payment | 3 |  |  | x
| 04.03 Add a new credit card | 2 |  |  | x
Module 5 - User's Account | 05.01 Create an Account
05.02 Sign into Account
| 05.03 Modify General User's Information | 1 |  | x
| 05.04 Review delivered and to be delivered items | 3 |  |  |  | x
| 05.05 Choose subscription plan | 4 |  | x
05.06 Contact a Customer Support
| 05.07 Delete an Account | 3 | x
|  | Velocity : | 11 | 11 | 10 | 10

## Road Map I2
ToGo Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/06/20 | Iteration 2 - 04/03/20 | Iteration 3 - 04/24/20 | Iteration 4 - 05/01/20
Module 1 - ToGo Delivery | 01.01 Mention the location of pickup | 3 | x
| 01.02 Mention the delivery location | 3 | x
Module 2- Item Details | 02.01 Enter details of the item | 2 | x
| 02.02 Enter the number of items to be delivered | 2 |  | x
| 02.03 Book a vehicle | 4 |  | x
Module 3 - Tracking orders | 03.01 Track the delivery status | 4 |  |  |  | x
| 03.02 Notification of the delivered item | 3 |  |  |  | x
Module 4 - Payment | 04.01 Payment Mode | 5 |  |  | x
| 04.02 Make a payment | 3 |  |  | x
| 04.03 Add a new credit card | 2 |  |  | x
Module 5 - User's Account | 05.01 Create an Account
05.02 Sign into Account
| 05.03 Modify General User's Information | 1 |  | x
| 05.04 Review delivered and to be delivered items | 3 |  |  |  | x
| 05.05 Choose subscription plan | 4 |  | x
05.06 Contact a Customer Support
| 05.07 Delete an Account | 3 | x
|  | Velocity : | 11 | 11 | 10 | 10

## Roles Traceability
To-Go Web Application
User Roles | 01.To-Go Delivery |  | 02. Item Details |  |  | 03.Tracking Orders |  | 04. Payment |  |  | 05. User's Account
| 01.01 Mention the location of pickup | 01.02 Mention the delivery location | 02.01 Enter the details of the item | 02.02 Enter the number of items to be delivered | 02.03 Book a vehicle | 03.01 Track the delivery status | 3.02 Notification of the delivered item | 04.01 Payment mode | 04.02 Make a payment | 04.03 Add a New Credit Card | 05.01 Create an Account | 05.02 Sign into Account | 05.03 Modify General User's Information | 05.04 Review delivered and to be delivered items | 05.05 Choose subscription plan | 05.06 Contact a Customer Support | 05.07 Delete an Account
Vendor Manager |  |  |  |  | X |  |  | X | [7 empty] | X
Delivery Manager | [5 empty] | X | X
Account Manager | [10 empty] | X | X | X | X | X |  | X
Subscribed User | x | x | x | x |  | x |  | x | x | x | X | X | X | X | X | X | X
Guest User | x | x | x | x |  | x |  | x | x | x | X | X | X | X | X | X | X
Finance Manager | [7 empty] | X | X | X

## Role Descriptions
USER ROLES
Vendor Manager
Includes working intimately with sellers to settle on buying choices and keeping up associations with merchants for whatever length of time that the organization utilizes them.
Delivery Manager
A person in a team who leads on agile and lean practices. They use variety of agile and lean tool and techniques in order to help the team keep a delivery and learning cadence that helps to remain focused. Responsible for tracking the various Scrum team efforts in an Agile way. Delivery Manager is responsible to the business owner and provides the business owner with the data needed to make decisions.
Account Manager
A person who works for a company and is responsible for the management of sales and relationship with particular customers. This roles is to ensure that client needs are understood and satisfied. They build and managed client relationships.collect information and ensurre that company. They build and manage client relationhips, collect information, and ensure that company offerings meet the individual eefs of client.
Subscribed User
A user whose role is to deliver additional content to users such as newsletter or access to the pages and posts that would otherwise be locked.Subscriber may also refer to a user who has subscribed to a website using RSS feed.
Guest user
A user role assigned to any client who associates to the guestnet SSID.The guest-logon user role is more restrictive than the logon role.
Finance Manager
A person in a team whose typical duties include reviewing financial reports,monitoring accounts and preparing activity reports and financial forecasts.